## Instructions
Deliverables Timeline (Gantt Chart)
Summary
A simple, excel Gantt chart to display project timelines and delays.
How to use
1. Add entries in 'Input' sheet to the next row in the table. Do not leave any blank rows in the middle. To delete rows, right click on the row(s) you wish to delete. Select delete and chose table row(s).
2. When adding entries only fill out the first 4 columns. The last 3 are automatically generated.
3. Look at the Gantt Chart in the 'Gantt' sheet. It should update to include your new deliverables. Now fix the date (x-axis) by right clicking on it, choosing 'Format Axis' and adjusting the minumum bounds and major units using the pane on the right. To help, the 'Input' sheet automatically calculates the 'Earliest Start' value for you to use as a minimum bound.
4. Copy and paste into your PowerPoint deck or medium of choice. Add "On Track, At Risk, Complete" icons to the right of the bars as needed. Lastly, copy over the slightly transparent dashed line and move it over to approximately the current day.
5. In your deck, add a text box and include the average delay to highlight the delay.

## Input
Do NOT edit these columns
Deliverable | Original Start | Original Target | Revised Target / Completion | Original Duration | Revised Duration | Delay | Average Delay | Earliest Start
Quadrotor Assembly | 2016-12-10 | 2017-01-20 | 2017-01-20 | 41 | 41 | 0 | -19456.4545 | 2016-12-10
Sensor and Flight Controller Integration | 2017-01-15 | 2017-01-25 |  | 10 | -42750 | -42760
SSE Sensor Offline Testing | 2017-01-21 | 2017-02-20 | 2017-02-20 | 30 | 30 | 0
SSE Hardware Testing | 2017-01-21 | 2017-02-20 | 2017-04-25 | 30 | 94 | 64
Software Integration | 2017-01-21 | 2017-04-09 |  | 78 | -42756 | -42834
Software Testing | 2017-02-01 | 2017-04-20 |  | 78 | -42767 | -42845
Spring Presentation | 2017-02-01 | 2017-02-15 |  | 14 | -42767 | -42781
Sensor Assembly on Quadrotor | 2017-02-15 | 2017-02-25 | 2017-02-25 | 10 | 10 | 0
SSE Real-Time Testing | 2017-02-20 | 2017-04-07 | 2017-04-07 | 46 | 46 | 0
Final Report | 2017-04-01 | 2017-05-05 | 2017-05-05 | 34 | 34 | 0
Final Presentation | 2017-05-05 | 2017-05-10 |  | 5 | -42860 | -42865
Formulas:
Earliest Start = MIN(GanttInput[Original Start])
Note on J4: Use this for the callout.
Note on K4: Use this for the min x-axis value

## Gantt
G
R
P
Y